## CutOver Plan
% Completed | Outline | Task | Predecessors | Responsible | Due Date | Time start | Time end | Duration
100% | 1 | Pre-Preparation
100% | 1.1 | Transports & User ID
100% | 1.1.1 | Finalise single SPDD TR transport |  | Alex | 2025-10-17 | 9:00 | 17:00 | 8:00
100% | 1.1.2 | Create SPAU TRs & prepare list of other TRs |  | Alex | 2025-10-23 | 15:00 | 15:30 | 0:30
100% | 1.1.3 | Create ECS_UPG1 User ID for SAP Upgrade team in PE1-100 |  | Vipin
100% | 1.2 | Jobs & interface
100% | 1.2.1 | Prepare list of jobs to run before downtime & after upgrade |  | Ashish/Uma | 2025-10-23 | 0:00 | 0:00 | 0:00
100% | 1.2.2 | Identify interfaces to stop / inform in SAP CPI |  | Uma | 2025-10-23 | 0:00 | 0:00 | 0:00
100% | 1.3 | Communications
100% | 1.3.1 | Align with 3rd party systems: NetOrder, MSD, Ehealth, .. |  | Various | 2025-10-23 | 0:00 | 0:00 | 0:00 | Check with all workstream | OTC | PTP | EWM | RTR
100% | 1.3.2 | Align with business on communications to customers & 3rd party |  | Lorenzo | 2025-10-23 | 0:00 | 0:00 | 0:00
100% | 1.3.3 | Create IT-CoE mail group |  | Nav | 2025-10-23 | 0:00 | 0:00 | 0:00 | S4H_ITCOE@covetrus.com
100% | 1.3.4 | Actions on jobs / interfaces - plan is clear? |  | All workstream | 2025-11-05 |  |  |  | Check with all workstream | OTC | PTP | EWM | RTR
100% | 2 | Preparation
100% | 2.1 | Go / No-Go decision |  | PMO | 2025-10-24 | 11:30 | 12:30 | 1:00
100% | 2.2 | Communications
100% | 2.2.1 | Inform SAP ECS upgrade team |  | Ashish | 2025-10-24 | 12:30 | 13:00 | 0:30 |  | Kentico |  | Modulix?
100% | 2.2.2 | Inform 3rd party resources |  | All workstream | 2025-10-24 | 12:30 | 17:00 | 4:30 | Check with all workstream | OTC | PTP | EWM | RTR
100% | 2.2.3 | Inform customers on the downtime/order earlier/receive later |  | Lorenzo | 2025-10-24 | 12:30 | 17:00 | 4:30
100% | 2.3 | Technical preparations - before handover to SAP | [5 empty] | 0:00
100% | 2.3.1 | Check for Open transports in System |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.2 | Import missing SAP Note( SNOTE - 3007754,3010852,3044634) |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.3 | Simplification item checklist - run report |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.4 | Eliminate duplicate entries from table /IWFND/I_MED_SRH (found from simplification list) |  | Alex | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.5 | Simplification item checklist - completion |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.6 | Technical checks & activities - Basis |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.6.1 | Check Locks and Update Requests (SM12/SM13) |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.6.2 | Queues in SMQ1/SMQ2 |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.6.3 | Check Hanging IDOCs |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.6.4 | Create file name /OTX/PF11_IES_SNAPSHOT_DIR for OpenText VIM Core Capture Profile Backup |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.6.5 | Database inconsistencies (DB02) |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.3.6.6 | Check Leftover SPAU |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.4 | Handover to SAP ECS for preparation |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.5 | Technical preparations - after handover | [5 empty] | 0:00
| 2.5.1 | Basis preprations
| 2.5.1.1 | SAP ECS Upgrade preparation |  | SAP ECS
100% | 2.5.1.2 | Review if emergency TR have any impact on upgrade TRs |  | Ashish | 2025-11-03 | 0:00 | 0:00
100% | 2.5.1.3 | Finalize all upgrade TRs |  | Ashish | 2025-11-03 | 0:00 | 0:00 | 0:00 |  | OTC | PTP | EWM | RTR | AUTH
100% | 2.5.2 | OTC preparations | [5 empty] | 0:00
100% | 2.5.2.1 | Review OTC TRs after ToC |  | Serim/Cosmin | 2025-11-03 | 0:00 | 0:00
100% | 2.5.2.2 | Mass update unloading points for NL customers and open sales orders |  | Cosmin | 2025-11-03 | 0:00 | 0:00 |  | Check with Cosmin
100% | 2.5.3 | PTP preparations | [5 empty] | 0:00
100% | 2.5.3.1 | Review PTP TRs after ToC |  | Baskaran | 2025-11-03 | 0:00 | 0:00
100% | 2.5.4 | EWM preparations |  | Rogier
100% | 2.5.4.1 | Review EWM TRs after ToC+C80 |  | Anish | 2025-11-03 | 0:00 | 0:00
100% | 2.5.5 | RTR preparations |  | Elena
100% | 2.5.5.1 | Review RTR TRs after ToC |  | Elena | 2025-11-03 | 0:00 | 0:00
100% | 2.5.5.1 | Review RTR-VIM TRs after ToC |  | Vikrant | 2025-11-03 | 0:00 | 0:00
100% | 2.5.6 | Security preparations |  | Vipin | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 2.5.6.1 | Review AUTH TRs after ToC |  | Vipin | 2025-11-03 | 0:00 | 0:00 | 0:00
98.03% | 3 | Production Upgrade
100% | 3.1 | Upgrade: Uptime activities | [5 empty] | 0:00
100% | 3.1.1 | SAP ECS: Uptime activities - Start |  |  | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 3.1.2 | Set System message in PE1 for Downtime |  | Ashish | 2025-11-03 | 0:00 | 0:00
100% | 3.1.3 | IT Team requests for Fire fighters |  | Vipin | 2025-11-03 | 0:00 | 0:00 | 0:00
100% | 3.1.4 | Lock phase (No TR including emergency TRs) |  | Ashish | 2025-11-06 | 0:00 | 0:00 | 0:00
100% | 3.2 | Upgrade: Downtime activities | [5 empty] | 0:00
100% | 3.2.1 | Business confirms close of business |  | Lorenzo
100% | 3.2.2 | OTC activities before downtime | [5 empty] | 0:00
100% | 3.2.2.1 | Update NL RDD table to change cutoff time |  | Joyce | 2025-11-07 | 9:00 | 9:00 | 0:00
100% | 3.2.2.2 | Close Kentico and inform Netorder to suspend order submit |  | Cosmin | 2025-11-07 | 16:30 | 16:35 | 0:05
100% | 3.2.2.3 | Run BE re-scheduling jobs |  | Serim | 2025-11-07 | 16:35 | 16:45 | 0:10
100% | 3.2.2.4 | Execute delivery jobs for NL and BE |  | Cosmin | 2025-11-07 | 16:45 | 16:55 | 0:10 | Re-scheduling job should be completed
100% | 3.2.2.6 | Run NL small order cost job - Z_SD_NL_SMALL_ORDER_COST |  | Harsha | 2025-11-07 | 16:45 | 16:50 | 0:05
100% | 3.2.2.7 | Run BE return fee job - ZSD_RETURN_FEE |  | Harsha | 2025-11-07 | 16:45 | 16:50 | 0:05
100% | 3.2.2.8 | NL BO output trigger job - Z_SD_NL_BO_OUTPUT_TRIGGER |  | Harsha | 2025-11-07 | 16:45 | 16:50 | 0:05 | Job Z_EWM_NL_ODO_PGI_TRIGGER should be completed
100% | 3.2.2.9 | Execute carrier report - Z_SD_CARRIER_PRE-ANN_RIT10010 |  | Harsha | 2025-11-07 | 16:45 | 16:50 | 0:05 | Job Z_EWM_NL_ODO_PGI_TRIGGER should be completed
100% | 3.2.2.5 | Run Netorder full stock interface job - Z_SD_BE_SEND_STOCK_BATCH_FULL |  | Cosmin | 2025-11-07 | 16:45 | 16:50 | 0:05 | Job Z_EWM_NL_ODO_PGI_TRIGGER should be completed
100% | 3.2.3 | PTP activities before downtime
100% | 3.2.3.1 | Run E3-Update Variant Jobs, both for BE and NL |  | Baskaran | 2025-11-07 | 16:15 | 16:17 | 0:02
100% | 3.2.3.2 | Prepone and Run the 16 , MM-E3 realted jobs and send files to E3 |  | Baskaran | 2025-11-07 | 16:30 | 16:45 | 0:15
100% | 3.2.3.3 | Z_MM_BE01_OUTOFSTOCK |  | Baskaran | 2025-11-07 | 16:15 | 16:30 | 0:15
100% | 3.2.3.4 | Z_MM_NL01_OUTOFSTOCK |  | Baskaran | 2025-11-07 | 16:30 | 16:45 | 0:15
100% | 3.2.3.5 | Z_MM_BE03_OUTOFSTOCK |  | Baskaran | 2025-11-07 | 16:45 | 16:50 | 0:05
100% | 3.2.3.6 | Run Job: Z_MM_NL_PR_PO_HILLS |  | Baskaran | 2025-11-07 | 16:45 | 16:50 | 0:05
100% | 3.2.3.7 | Run Job: Z_MM_NL_SEND_PO_TO_HILLS |  | Baskaran | 2025-11-07 | 16:50 | 16:55 | 0:05
100% | 3.2.3.8 | Run Job: ZMM_E3_CHANGE_LOG_CLEANING |  | Baskaran | 2025-11-07 | 16:50 | 17:00 | 0:10
100% | 3.2.3.9 | Last received ASN and Order Confirmation from Pajero |  | Baskaran | 2025-11-07 | 16:15 | 16:30 | 0:15
100% | 3.2.3.10 | Last received ASN from Animal Care |  | Baskaran | 2025-11-07 | 16:15 | 16:30 | 0:15
100% | 3.2.3.11 | Run Stock Values (MB5L) before Down Time |  | Baskaran | 2025-11-07 | 16:15 | 16:45 | 0:30
100% | 3.2.3.12 | Run Stock on Posting Date (MB5B) before Down Time |  | Baskaran | 2025-11-07 | 16:15 | 16:45 | 0:30
100% | 3.2.4 | EWM activities before downtime
100% | 3.2.4.1 | Run job Z_EWM_NL_ODO_PGI_TRIGGER |  | Rogier | 2025-11-07 | 16:30 | 16:45 | 0:15
100% | 3.2.4.2 | Run job Z_EWM_NL_AUTOGI |  | Rogier | 2025-11-07 | 16:45 | 17:00 | 0:15
100% | 3.2.4.3 | Check if operations have finished (No more open tasks in Modulix) |  | Rogier | 2025-11-07 | 16:30 | 17:00 | 0:30
100% | 3.2.4.4 | Check open WO/WT for NL & BE |  | Rogier | 2025-11-07 | 16:30 | 17:00 | 0:30
100% | 3.2.4.5 | Check SMQ1 / SMQ2 |  | Rogier | 2025-11-07 | 16:30 | 17:00 | 0:30
100% | 3.2.5 | RTR activities before downtime
100% | 3.2.5.1 | RTR - Export Trial Balance before system downtime -> before 3.2.7.2 user lock |  | Ronny&Joyce | 2025-11-07 | 17:00 | 17:30 |  | Depends on the other stream completion
100% | 3.2.5.2 | Export Chart of Accounts backup SKA1, SKB1, SKAT |  | Elena | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.3 | Run check BSEG / BKPF / FAGLFLEXA / ACDOCA / ACDOCU (number of records) |  | Elena | 2025-11-07 | 17:00 | 17:10 |  | Depends on the other stream completion
100% | 3.2.5.4 | Export open items: vendors, customers, gl (total amount and items per company) |  | Elena | 2025-11-07 | 17:10 | 17:20 |  | Depends on the other stream completion
100% | 3.2.5.5 | Export of trial balances (company code level) |  | Elena | 2025-11-07 | 17:20 | 17:35 |  | Depends on the other stream completion
100% | 3.2.5.6 | Check last depreciation run (AFABN) successfully posted |  | Elena | 2025-11-07 | 16:45 | 16:50
100% | 3.2.5.7 | Export of Financial Statement |  | Elena | 2025-11-07 | 17:35 | 17:50 |  | Depends on the other stream completion
100% | 3.2.5.8 | Check last payment runs (F110) and last bank integrations (EBS) |  | Elena | 2025-11-07 | 16:50 | 17:00
100% | 3.2.5.9 | Check number ranges and posting period variant (all) SE16N |  | Elena | 2025-11-07 | 17:50 | 18:00 |  | Depends on the other stream completion
100% | 3.2.5.10 | VIM Execute Jobs before Downtime |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.11 | Z_VIM_VENDOR_DOWNLOAD |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.12 | Z_VIM_RELEASE BLOCKS MM |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.13 | Z_VIM_PO_DOWNLOAD |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.14 | Z_VIM_HEADER_WORKFLOW |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.15 | Z_VIM_CENTRAL_REPORTING_2 |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.16 | Z_VIM_VENDOR_DOWNLOAD_2 |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.17 | Z_VIM_CENTRAL_REPORTING_1 |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.18 | Z_VIM_RESTART_WORKITEM |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.19 | Z_FI_BE_VIM_POST |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.20 | Z_VIM_REREUN_RULES |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.21 | Z_VIM_RERUN_RULES_2 |  | Vikrant | 2025-11-07 | 16:30 | 16:45
100% | 3.2.5.22 | VIM Create a ML snapshot for Capture Profile |  | Vikrant | 2025-11-07 | 17:00 | 0:00 | 0:00 | After User are blcoked and before SAP starts upgrade
100% | 3.2.5.23 | VIM Download the ML snapshot |  | Vikrant | 2025-11-07 | 17:00 | 0:00 | 0:00 | After User are blcoked and before SAP starts upgrade
100% | 3.2.5.24 | VIM Download COA backup |  | Vikrant | 2025-11-07 | 17:00 | 0:00 | 0:00 | After User are blcoked and before SAP starts upgrade
100% | 3.2.5.25 | VIM Check any last extractions requests |  | Vikrant | 2025-11-07 | 17:00
100% | 3.2.5.26 | Wholesale - Stop Document Send Process |  | Tracy | 2025-11-07 | 12:00 | 0:00 | 0:00
100% | 3.2.6 | Security activities before downtime
100% | 3.2.6.1 | Get list of users currently active |  | Vipin | 2025-11-07 | 12:00 | 0:00 | 0:00
100% | 3.2.7 | Basis, Security & Integration activities before downtime
100% | 3.2.7.1 | Post a SM02/system message to log off users |  | Ashish | 2025-11-07 | 17:00 | 17:00
100% | 3.2.7.2 | Lock dialog users except CoE users & default users - should be done ONLY after green light from all team |  | Vipin | 2025-11-07 | 17:00 | 17:00
100% | 3.2.7.3 | Check SMQ1 / SMQ2 / IDOC….... |  | Ashish | 2025-11-07 | 17:00 | 17:00 |  | Contact Rogier/Adil
100% | 3.2.7.4 | Run jobs before downtime |  | Ashish | 2025-11-07 | 17:00 | 17:00
100% | 3.2.7.5 | Suspend all jobs BTCTRNS1 |  | Ashish | 2025-11-07 | 17:00 | 17:00 | 0:00
100% | 3.2.7.6 | Process Inbound/Outbound Queues (SMQ1 & SMQ2) |  | Ashish | 2025-11-07 | 17:00 | 17:00
100% | 3.2.7.7 | Process all IDOCS (BD64 SM58 etc.) |  | Ashish | 2025-11-07 | 17:00 | 17:00
100% | 3.2.7.8 | Check and take the necessary action for failed and active updates and locks (SM12/SM13) |  | Ashish | 2025-11-07 | 17:00 | 17:00
100% | 3.2.7.9 | Check if Any Active job in SM37 |  | Ashish | 2025-11-07 | 17:00 | 17:00
100% | 3.2.7.10 | Stop Inbound/Outbound Queues if any |  | Ashish | 2025-11-07 | 17:00 | 17:00
100% | 3.2.7.11 | Stop SAP CPI interfaces (inbound & outbound) |  | Uma | 2025-11-07 | 17:00 | 17:00
100% | 3.2.7.6 | Inform SAP ECS to start upgrade - downtime activities |  | Ashish | 2025-11-07 | 17:00 | 17:00 | 0:00
100% | 3.2.7.7 | SAP ECS starts downtime |  | Ashish | 2025-11-07 | 17:00 | 17:00
100% | 3.2.8 | Communications - start of downtime |  | Nav
92.59% | 3.3 | Post upgrade - technical checks |  | Ashish |  |  |  | 0:00
100% | 3.3.1 | SAP ECS completes upgrade |  | Ashish | 2025-11-08 | 15:00 | 15:00 | 0:00
100% | 3.3.2 | Check SAP ECS has triggered online back-up |  | Ashish | 2025-11-08 | 15:00 | 15:00
0% | 3.3.3 | Technical validation - Basis |  | Ashish | 2025-11-08 | 15:00 | 15:00 | 0:00
100% | 3.3.3.1 | Execute T-Code Sick |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.2 | Execute T-Code SCC4. Check Client setting should be same as before Upgrade |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.3 | Check in SM51. All application server should be Active |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.4 | Check SMICM. All protocol should be active or status should be as before Upgrade |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.5 | Validate SOST |  | Ashish | 2025-11-08 | 15:00 | 15:00
0% | 3.3.3.6 | Execute transaction RZ10 & check active profile version. Should be same as before Upgrade |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.7 | Execute STMS -> TMS Should be active. |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.8 | Execute SM61 and check BG Job Server Groups |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.9 | Check RFC Destination |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.10 | Check Spool Servers |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.11 | Check Logon Group. T-Code : SMLG |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.12 | Check SOAMANAGER Configuration |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.13 | Check Update server is active. T-Code : SM13 |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.14 | Check Repository connectivity. T-Code : OAC0 |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.15 | Validate ADS Connection |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.16 | Validate DBACOCKPIT |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.3.17 | Check Fiori Link is working |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.4 | Open PE1 production system for configuration |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.5 | Verify Bex - BW apps are working or not |  | Ashish | 2025-11-08 | 15:00 | 15:00 | 0:00
100% | 3.3.6 | Issue Fix - My inbox app is not working(S4UP-99) |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.7 | Change setting for Repository DMS_C1(S4UP-1255) |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.3.8 | Close PE1 production system for configuration |  | Ashish | 2025-11-08 | 15:00 | 15:00 | 0:00 | Are there any activities below which need client opening?
100% | 3.3.9 | Technical validation - ABAP (soamanager) |  | Ashish/Alex | 2025-11-08 | 15:00 | 15:00 | 0:00
100% | 3.3.10 | Technical validation - CPI connectivity |  | Uma/Josh | 2025-11-08 | 15:00 | 15:00 | 0:00
99.52% | 3.4 | Post upgrade - transports & manual activities | [5 empty] | 0:00
99.38% | 3.4.1 | Basis & technical post upgrade activities | [5 empty] | 0:00
100% | 3.4.1.1 | CVET Basis - Import SPAU |  | Ashish/Alex | 2025-11-08 | 15:00 | 15:00
95% | 3.4.1.2 | CVET Basis - Upgrade TRs |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.4.1.3 | Execute the report RSBCS_NUMBER_RANGE manually.(S4UP-84) |  | Ashish/ Serim | 2025-11-08 | 15:00 | 15:00
100% | 3.4.1.4 | Maintain Customizing for storage category" for change inbound delivery app(S4UP-1141) |  | Ashish/Rogier | 2025-11-08 | 15:00 | 15:00
100% | 3.4.1.5 | Maintain the settings in transaction /n/UI2/FLP_SYS_CONF (Ref-S4UP-495) |  | Ashish | 2025-11-08 | 15:00 | 15:00
100% | 3.4.1.6 | RTR: Activate structures, Regenerate and Activate Operating Concern KEA0 |  | Elena | 2025-11-08 | 17:00 | 17:15 | 0:15
100% | 3.4.1.7 | Perform SM59 Ping Test from PE1 to CPI |  | Ashish/Uma | 2025-11-08 | 15:00 | 15:00
100% | 3.4.1.8 | Start SAP CPI Interfaces |  | Ashish/Uma | 2025-11-09
100% | 3.4.2 | OTC post upgrade activities
100% | 3.4.2.1 | Run tcode BUSP - OSS note 1621119 |  | Cosmin | 2025-11-09 | 9:00 | 9:30
100% | 3.4.2.2 | Acitivate services in SICF - *ATP* , LIBREVALLOCCS1, SUPPROTRACRS1 |  | Serim | 2025-11-09 | 9:00 | 9:30
100% | 3.4.2.3 | Active service SD_LIBBILCOMS1 |  | Serim | 2025-11-09 | 9:00 | 9:30
100% | 3.4.3 | PTP post upgrade activities - none
100% | 3.4.4 | EWM post upgrade activities - none
99.17% | 3.4.5 | RTR post upgrade activities
100% | 3.4.5.1 | Run program for Regeneration of ABAP Coding for Validations/Substitutions/Rules RGUGBR00 |  | Elena | 2025-11-08 | 17:15 | 17:25
100% | 3.4.5.2 | Run program for Correction/Change/Activate/Repair special fields RFPOSXEXTEND |  | Elena | 2025-11-08 | 17:25 | 17:35
100% | 3.4.5.3 | Run program for Reset ALV buffer BALVBUFDEL |  | Elena | 2025-11-08 | 17:35 | 17:45
100% | 3.4.5.5 | VIM Create an Inbound Destination & Scheduler |  | Vikrant | 2025-11-08 | 19:00 |  | 0:10
95% | 3.4.5.6 | VIM Schedule New Staging Jobs |  | Vikrant | 2025-11-08 | 19:00 |  | 1:00
100% | 3.4.5.7 | VIM Update & Reactivate Capture Profile with snapshot |  | Vikrant | 2025-11-08 | 19:00 |  | 0:15
100% | 3.4.6 | Security post upgrade activities | [5 empty] | 0:00
100% | 3.4.6.1 | Create CMS_MS user |  | Vipin |  |  |  | 0:00
100% | 3.4.6.2 | Follow the instruction 2827260 - Configuration steps for /sap/bc/contentserver service |  | Alex |  |  |  | 0:00
100% | 3.4.7 | Final - Basis & technical post upgrade activities
100% | 3.4.7.1 | Regen program RV80HGEN for ABAP |  | Ashish | 2025-11-09 | 11:00 | 11:00
100% | 3.4.7.2 | Fiori index regeneration? /UI5/APP_INDEX_CALCULATE |  | Alex | 2025-11-09 | 11:00 | 11:00
100% | 3.4.7.3 | removing cache, etc? |  | Ashish | 2025-11-09 | 11:00 | 11:00
64.72% | 4 | Post Upgrade validations
88.1% | 4.1 | Functional & Technical validations | [5 empty] | 0:00
100% | 4.1.1 | Checks by OTC | [5 empty] | 0:00
100% | 4.1.1.1 | Check main OTC tables and transactions |  | Cosmin/Harsha/Serim | 2025-11-09 | 9:00 | 12:00
100% | 4.1.1.2 | Verify Invoice email output for the old invoices |  | Harsha | 2025-11-09 | 9:30 | 10:00
0% | 4.1.2 | Checks by PTP | [5 empty] | 0:00
100% | 4.1.2.1 | Check the App: Monitor PO Items |  | Baskaran | 2025-11-09 | 9:30 | 9:45
100% | 4.1.2.2 | Check the important MM related transactions |  | Baskaran | 2025-11-09 | 9:45 | 10:45
100% | 4.1.2.3 | Run Stock Values (MB5L) after Down Time and compare with before Down Time |  | Baskaran | 2025-11-09 | 10:45 | 11:15
100% | 4.1.2.4 | Run Stock on Posting Date (MB5B) after Down Time and compare with before Down Time |  | Baskaran | 2025-11-09 | 11:15 | 11:45
0% | 4.1.3 | Checks by EWM | [5 empty] | 0:00
100% | 4.1.3.1 | Check its mobile on RF device |  | Rogier
0% | 4.1.3.2 | Check Modulix interface |  | Rogier
100% | 4.1.3.3 | Check FMD warehouse settings BRF+ |  | Rogier
100% | 4.1.3.4 | Check distr model BD64 |  | Rogier
97.83% | 4.1.4 | Checks by RTR | [5 empty] | 0:00
100% | 4.1.4.1 | Verify chart of accounts, ledgers, and fiscal year variants FINSC_LEDGER |  | Elena | 2025-11-08 | 19:00
100% | 4.1.4.2 | Compare Trial Balance pre- vs post-upgrade |  | Elena | 2025-11-08 | 19:00
100% | 4.1.4.3 | Compare open items pre- vs post-upgrade | Differences found. Reason sales posted friday with future date 08.11.2025. OK | Elena | 2025-11-08 | 19:00
100% | 4.1.4.4 | Check financial statement versions pre- vs post-upgrade F.01 |  | Elena | 2025-11-08 | 19:00
100% | 4.1.4.5 | Check last payment runs (F110) and last bank integrations (EBS) pre- vs post-upgrade |  | Elena | 2025-11-08 | 19:00
100% | 4.1.4.6 | Check last depreciation run (AFABN) pre- vs post-upgrade |  | Elena | 2025-11-08 | 19:00
100% | 4.1.4.7 | Check number ranges and posting period variant (all) pre- vs post-upgrade SE16N | Differences found NRIV table | Elena | 2025-11-08 | 19:00
100% | 4.1.4.8 | Check BSEG / BKPF / FAGLFLEXA / ACDOCA / ACDOCU (number of records) pre- vs post-upgrade SE16H |  | Elena | 2025-11-08 | 19:00
100% | 4.1.4.9 | RTR - Check Trial Balance compare pre vs post-upgrade -> before jobs start and smoke test starts |  | Ronny | 2025-11-09 | 12:30
100% | 4.1.4.10 | VIM Check Archive Connectivity |  | Vikrant | 2025-11-09
100% | 4.1.4.11 | VIM Check connectivity with the Core Capture |  | Vikrant | 2025-11-09
100% | 4.1.4.12 | VIM Check Status of Capture Profile |  | Vikrant | 2025-11-09
50% | 4.1.4.13 | VIM Smoke Test - Process Invoice Inbound via Email for both BE and NL Email addresses |  | Joyce | 2025-11-09
100% | 4.1.4.14 | Process Master Data ALE Connection - GLMAST, GLCORE, PRCMAS, COSMAS |  | Tracy Stevenson | 2025-11-09 |  |  |  | Test GL Jira Tickets available for this testing -SE1-QE1-PE1 for smoke testing wait for Ashish to set this up (until DE1 becomes available)
100% | 4.1.4.15 | Run UK Custom Reports - Customer Aging Report - Credit Utilisation |  | Tracy Stevenson | 2025-11-09
100% | 4.1.4.16 | Send Wholesale Accounting Docs |  | Tracy Stevenson | 2025-11-09
100% | 4.1.4.17 | Wholesale - Restart Document Send Process |  | Tracy Stevenson | 2025-11-10 |  |  |  | Sample documents to be sent as part of Smoke Test
100% | 4.1.4.18 | Check unavailable apps / deprecated apps / available with successor | 2 topics identified. Not critical. Jira incident will be opend to vipin | Elena | 2025-11-09
100% | 4.1.4.19 | Smoke Test - Electronic Bank statement import (FF_5) and processing (FEBAN) |  | Joyce | 2025-11-09
100% | 4.1.4.20 | Smoke Test - Customer Invoice FI (FB70) |  | Joyce | 2025-11-09
100% | 4.1.4.21 | Smoke Test - Vendor Invoice (MIRO) |  | Joyce | 2025-11-09
100% | 4.1.4.22 | Smoke Test - payment run (F110) and import file in ING bank |  | Joyce | 2025-11-09
100% | 4.1.4.23 | Smoke Test - dunning (F150) and Account statement (F.27) |  | Joyce | 2025-11-09
0% | 4.1.5 | Checks by Technical | [5 empty] | 0:00
0% | 4.1.5.1 | none
0% | 4.1.6 | Checks by Security | [5 empty] | 0:00
0% | 4.1.6.1 | none
0% | 4.2 | Prepare for release to business | [5 empty] | 0:00
0% | 4.2.1 | Unlock all dialog users |  | Vipin |  |  |  | 0:00
0% | 4.2.2 | Smoke test |  | Business
0% | 4.2.4 | Inform all users & 3rd-party |  | Lorenzo/Nav |  |  |  | 0:00
0% | 4.3 | Run jobs after smoke test confirmation |  |  | 2025-11-09 |  |  | 0:00
100% | 4.3.1 | OTC exception activities - Run jobs & checks
100% | 4.3.1.1 | Update NL RDD table to change cutoff time |  | Joyce | 2025-11-09 | 16:00 | 16:30
100% | 4.3.1.2 | Job Z_SD_NL_3PL_SND-OVERVIEW should be executed with Friday data |  | Serim | 2025-11-09 | 16:00 | 16:30
100% | 4.3.1.3 | Job ZSD_SO_EMAIL_IVC should be executed with Friday data |  | Serim | 2025-11-09 | 16:00 | 16:30
100% | 4.3.1.4 | Job Z_SD_BE_INVOICE_CREATE should be executed |  | Cosmin | 2025-11-09 | 16:00 | 16:30
100% | 4.3.1.5 | Job Z_SD_NL_INVOICE_CREATE should be executed |  | Cosmin | 2025-11-09 | 16:00 | 16:30
100% | 4.3.1.6 | Job Z_SD_NL_INVOICE_OUTPUT_TRIGGER should be executed |  | Cosmin | 2025-11-09 | 16:00 | 16:30
0% | 4.3.2 | PTP exception activities - Run jobs & checks
0% | 4.3.2.1 | Run MM related CPI jobs to process the MSD files , which are received during S4H-Down Time |  | Baskaran / Uma | 2025-11-09 | 16:00 | 16:30
0% | 4.3.2.2 | Process the ASN messages from Pagero, which are received during S4H-Down Time |  | Baskaran / Uma | 2025-11-09 | 16:00 | 16:30
0% | 4.3.2.3 | Process the ASN messages from Animal care, which are received during S4H-Down Time |  | Baskaran / Uma | 2025-11-09 | 16:00 | 16:30
100% | 4.3.3 | RTR exception activities - Run jobs & checks
100% | 4.3.3.1 | Job Z_SD_EU_COPA should be executed |  | Ashish | 2025-11-09
0% | 4.3.4 | EWM exception activities - Run jobs & checks
0% | 4.3.4.1 |  |  | Rogier
0% | 4.3.5 | Basis - Release all jobs & checks
0% | 4.3.5.1 | Release all jobs |  | Ashish | 2025-11-09
0% | 4.4 | Go-Live OR Fall-back |  |  | 2025-11-09 |  |  | 0:00
0% | 4.4.1 | Go Live |  | Nav |  |  |  | 0:00
0% | 4.4.2 | Fall-back |  | Nav |  |  |  | 0:00
| 5 | Hypercare
| 5.1 | BAU Business validations - Post Go-Live | [5 empty] | 0:00
| 5.1.1 | Validations by Business users - UK | [5 empty] | 0:00
| 5.1.2 | Validations by Business users - DE/AT | [5 empty] | 0:00
100% | 5.1.3 | BeNe Tableau |  | Uma |  |  |  | 0:00
100% | 5.1.4 | BeNe salesforce |  | Uma |  |  |  | 0:00
100% | 5.1.5 | Snowflake |  | Uma |  |  |  | 0:00
100% | 5.1.6 | E3 interfaces |  | Uma |  |  |  | 0:00
100% | 5.1.7 | EDI: Pagero |  | Uma |  |  |  | 0:00
80% | 5.1.8 | EDI: Animal care |  | Uma |  |  |  | 0:00
| 5.2 | Start Development upgrade | [5 empty] | 0:00

## GO-Live weekend
Teams availaiblity over the weekend
Saturday all remote
IT COE | BE | NL | Remote
Cosmin Martin <cosmin.martin@maravet.com> | x
Elena-Iuliana Mazilu <elena-iuliana.mazilu@covetrus.com> |  |  | x
Alexandru Costea <alexandru.costea@maravet.com> |  | x
Adil Mouslim <adil.mouslim@covetrus.com> | x
Anish Balachandran <anish.balachandran@covetrus.com> |  |  | x
Vikrant Patil <vikrant.patil@covetrus.com> |  |  | x
Tracy Stevenson <tracy.stevenson@covetrus.com> |  |  | x
Rogier Huizing <rogier.huizing@covetrus.com> |  | x
Baskaran Srinivasan <Baskaran.Srinivasan@covetrus.com> |  |  | x
Rajesh Avinjikat <rajesh.avinjikat@covetrus.com> |  | x
Harsha Vardhan Reddy Bobbala <harshavardhanreddy.bobbala@covetrus.com> |  |  | x
Ashish Bamane <Ashish.Bamane@covetrus.com> |  |  | x
Joshpeter Ramanathan <Joshpeter.Ramanathan@covetrus.com> |  | x
Uma Chougule <uma.chougule@covetrus.com> |  |  | x
Vipin Yadav <Vipin.Yadav@covetrus.com> |  |  | x
Serim Sari <serim.sari@covetrus.com> |  | x
Nav Singh |  | x
Lorenzo | x
Astrid |  | x
Business teams
Kobie Eerdekens (OTC) | x
Lara Nuyts (OTC) | x
Tanja Vanspauwen (EWM) | x
Miet Moors (EWM) | x
Ken Henrotte (EWM) | x
Pieter Driesen (EWM) | x
Tom Moors (EWM) | x
Franco Zito (EWM) | x
Bart Vandebeek (EWM) | x
Ilse Vanempten (EWM) | x
Raf Put (EWM) | x
Jelle Claes (PTP) | x
Emmely Snoeks (PTP) | x
Katrien Verhagen (MD) | x
Ronny Ebbers (RTR) |  | x
Joyce Hopman (RTR) |  | x
Rene Fleuren (RTR) |  | x
Bart vd Boom (EWM) |  | x
Aurimas Budvytis (EWM) |  | x
Gaby Mijnders (EWM) |  | x
Hajira Tmimi (EWM) |  | x
Inge de Beer (EWM) |  | x
Reno van Dreumel (EWM) |  | x
Justin Muskens (EWM) |  | x
Mayke Coopmans (OTC) |  | x
Joyce Muis (OTC) |  | x

## Auth TRs
SE1K900102 | TOC-[AUTH] S4 Upgrade: Catalogs & Groups updated | 1 | SE1K900229 | Merge transport | 1
SE1K900244 | S4UP-88: ATPCheck issue in VA01 | 2
SE1K900211 | [Upgrade] Security role fixes | 2
SE1K900246 | [Upgrade] Security role fixes v2 | 2
SE1K900272 | Auth : S4UP-350 RTR app fix | 2
SE1K900274 | Auth 350 : security changes | 2
SE1K900294 | TOC : S4UP-495 Open Fiori A | 2
SE1K900299 | S4UP-11 Auth Mass tcode su24 with object F_LF | 2
SE1K900303 | S4UP-11 Auth Mass tcode su24 with object F_LF | 2
SE1K900305 | S4UP-11 Auth Mass tcode su24 with object F_LF | 2
SE1K900307 | S4UP-11 Auth Mass tcode su24 with object F_LF | 2
SE1K900322 | S4UP-984 Auth: update VL06 with new objects | 2
SE1K900324 | S4UP-984 Auth: update VL06 with new objects | 2
SE1K900339 | auth upgrade 1156 update tcode MASS with object f_lfa1_app | 2
SE1K900341 | auth upgrade 1156 update tcode MASS with object f_lfa1_app | 2
SE1K900349 | AUTH-982 : ADD FS-XXXXXXX-WM-DIS-AUTO-STOCK TO sUP ROLE | 2
SE1K900351 | AUTH-UP1074: NOT ABLE TO OPEN WAREHOUSE TASK | 2
SE1K900355 | S4UP-1174 Auth: update /SCWM/DLV2 with PDI | 2
SE1K900357 | AUTH S4UP: 1231: update object S_DMC_S_R | 2
SE1K900359 | auth s4up:1141: added 01 in /SCWM/ATTS | 2
SE1K900385 | auth: 1217: app F1751 (Credit Limit Utilization (S/4HANA) | 2
SE1K900393 | auth 1257: add ZUI_ATPSELECTOPTIONTOO | 2
SE1K900414 | AUTH 1217:app F1751 fix | 2
SE1K900424 | auth 1293: add ZVEN in role | 2
SE1K900434 | auth 1302: 3027 and 3029 in k_cca | 2
SE1K900444 | auth 1297: add C_CABN | 2
SE1K900442 | auth 1297: add C_CABN | 2
SE1K900455 | auth 1269: add deletion option to enable blocks | 2
SE1K900457 | auth 1305: added new service for F3616 | 2
SE1K900459 | AUTH 1299: VIEW LOGS AUTOMATIC PAY | 2
SE1K900461 | auth 1212: add tcode S_ALR_87012082 | 2
SE1K900477 | auth: 1248: add s_dataset for S_ALR_87009940_BE | 2
SE1K900475 | auth: 1248: add s_dataset for S_ALR_87009940_BE | 2
SE1K900482 | auth 1322: add trial balance app | 2
SE1K900491 | auth 1325: add tcode ZPTP_PRICING | 2
SE1K900498 | AUTH 1299: UPDATE S_DATASET | 2
SE1K900516 | auth 1161: add f_bkpf_koa | 2
SE1K900514 | auth 1161: add f_bkpf_koa | 2
SE1K900518 | auth 1340: semantic mapping correction for CXCD | 2
SE1K900527 | auth 1255: add statuatory reports | 2
SE1K900438 | 1346 - 3341894 - Syntax error on CL_GRAC_OIF_ERM_ROLEDEF | 2
SE1K900534 | auth 1255: f1515 app fix | 2
SE1K900545 | Auth 1255: Fix application job F1240 | 2
SE1K900552 | auth 1323 : Update kokrs to * in GR roles | 2
SE1K900642 | Auth : 1255: stat run report | 2

## CPI intefaces
CPI PROD Active Interfaces | Interface Executed Post Upgrade? Yes/No | Workstream | Sender | Sender Adapter | Receiver | Receiver Adapter | Triggered By ? Sender/ CPI Timer/ S4 Program | S4 Program | Related iFlows | Undeploy/ Deploy during PE1 Downtime? | Interface Stopped (Yes/No) | Smoke Test (Success/Failed) | Post Upgrade / Status of CPI Int. Started ( Yes/No)
PRD_AnimalCare_S4H_ASN | Yes | PTP(Baskaran) | AnimalCare | HTTPS | S4 | Idoc | Sender | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
PRD_AnimalCare_S4H_OrderResponse | Yes | PTP(Baskaran) | AnimalCare | HTTPS | S4 | Idoc | Sender | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_AnimalCare_Order | Yes | PTP(Baskaran) | S4 | Process Direct | HTTPS | AnimalCare | S4 Program | ? | Z_CPI_IDoc_CommonFlow Z_NL_S4H_Orders_Dispatcher | TBD / No need to undeploy as there will be no trigger from S4 | NA
Receive_AccountsReceivable_From_Wholesale_To_S4HANA | Yes | RTR(Tracy) | Wholesaler | SOAP | S4 | Idoc | Sender | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_E3Catalyst_Material | Yes | PTP(Baskaran) | S4 | HTTPS | E3 | SFTP | CPI Timer-Monday to Friday 2:00AM CET | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_EU_E3_PurchaseRequisition_S4 | Yes | PTP(Baskaran) | E3 | SFTP | S4 | SOAP | Sender-SFTP Polling Every 5min | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_E3_PurchaseRequisition_S4 | Yes | PTP(Baskaran) | E3 | SFTP | S4 | SOAP | Sender-SFTP Polling Every 5min | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_BE_E3_Deal File_To_S4 | Yes | PTP(Baskaran) | E3 | SFTP | S4 | SOAP | Sender-SFTP Polling Every 1min | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_BE_S4_DealFile_To_E3 | Yes | PTP(Baskaran) | S4 | SOAP | E3 | SFTP | S4 Program | ? | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_EU_S4_BookingFile_To_E3 | Yes | PTP(Baskaran) | S4 | SOAP | E3 | SFTP | S4 Program | ? | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_EU_S4_DailyItemStockStatus_To_E3 | Yes | PTP(Baskaran) | S4 | SOAP | E3 | SFTP | S4 Program | ? | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_EU_S4_ItemDiscount_To_E3 | Yes | PTP(Baskaran) | S4 | SOAP | E3 | SFTP | S4 Program | ? | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_EU_S4_MaterialDescription_To_E3 | Yes | PTP(Baskaran) | S4 | SOAP | E3 | SFTP | S4 Program | ? | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_EU_S4_MaterialOutbound_To_E3 | Yes | PTP(Baskaran) | S4 | SOAP | E3 | SFTP | S4 Program | ? | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_EU_S4_OrderExpedite_To_E3 | Yes | PTP(Baskaran) | S4 | SOAP | E3 | SFTP | S4 Program | ? | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_EU_S4_ReceivingFile_To_E3 | Yes | PTP(Baskaran) | S4 | SOAP | E3 | SFTP | S4 Program | ? | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_EU_S4_VendorFile_To_E3 | Yes | PTP(Baskaran) | S4 | SOAP | E3 | SFTP | S4 Program | ? | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
S4H_SnowFlake_Customer_BE | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Monday 12:00AM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_Customer_NL | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Sunday 11:40PM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_Invoice_BE | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Monday 03:40AM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_Invoice_NL | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Monday 04:30AM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_Manufacturer_BE_NL | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Sunday 10:40PM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_PO_BE | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Sunday 10:00PM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_PO_NL | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Sunday 09:00PM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z1001_S4H_SnowFlake_Product_BE | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Sunday 11:20PM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z1001_S4H_SnowFlake_Product_NL | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Sunday 11:00PM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_PriceList_BE | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Month Starting from 2025-08-09 04:00AM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_SalesOrder_BE | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Monday 04:20 AM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_SalesOrder_NL | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Monday 04:11 AM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_Supplier_BE | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Sunday 10:00 PM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_Supplier_NL | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Sunday 10:20 PM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_SupplierInvoice_BE | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Monday 03:00 AM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_SnowFlake_SupplierInvoice_NL | Yes | PTP(Baskaran) | S4 | HTTPS | SnowFlake | AmazonWebServices | CPI Timer-Every Monday 02:30 AM UTC | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_Tableau_Purchaseprice_BE | Yes | PTP(Baskaran) | S4 | Odata | Tableau | JDBC | CPI Timer-1:45AM CET | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
S4H_Tableau_Purchaseprice_NL | Yes | PTP(Baskaran) | S4 | Odata | Tableau | JDBC | CPI Timer-8:15AM CET | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_BE_S4H_CustomerMaster_To_SalesforceTableau | Yes | OTC | S4 | Odata | SalesForce, Tableau | Salesforce, JDBC | S4 Program Delta Load Every Hour - From 10:00AM CET to 11:00PM CET Full Load - 12:10AM CET | ZSD_SF_CUSTOMER_ACC_BE_DAILY | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BE_S4H_Deliveries_To_SalesForce | Yes | OTC | S4 | Odata | SalesForce | Salesforce | S4 Program | ? | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BE_S4H_ProductMaster_To_SalesForceTableau | Yes | PTP(Baskaran) | S4 | Odata | SalesForce, Tableau | Salesforce, JDBC | S4 Program Full Load - 12:46AM CET | ZMM_SF_PRODUCT_MASTER_BE | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BE_S4H_Salesorder_To_SalesForce | Yes | OTC | S4 | Odata | SalesForce | Salesforce | S4 Program | ZSD_SEND_TABLEAU_SAL_DETAILS | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BE_S4H_VendorMaster_To_SalesForceTableau | Yes | PTP(Baskaran) | S4 | Odata | SalesForce, Tableau | Salesforce, JDBC | S4 Program Full Load - 12:10AM CET | ZMM_SF_VENDOR_INTERFACE | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_NL_S4H_ProductMaster_To_SalesForce_Tableau | Yes | PTP(Baskaran) | S4 | Odata | SalesForce, Tableau | Salesforce, JDBC | S4 Program Full Load - 12:46AM CET | ZMM_SF_PRODUCT_MASTER_BE | Z_NL_S4H_Pricebook_To_SalesForce | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_NL_S4H_Pricebook_To_SalesForce | Yes | PTP(Baskaran) | S4 | Process Direct | Salesforce | Salesforce | S4 Program Full Load - Between 3:28AM to 3:40AM CET | ZMM_SF_PRODUCT_MASTER_BE | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_NL_S4H_CustomerMaster_To_Salesforce_TABLEAU | Yes | OTC | S4 | Odata | SalesForce, Tableau | Salesforce, JDBC | S4 Program Full Load - Between 3.15AM to 3:24AM CET | ZSD_SF_CUSTOMER_MASTER_NL_IF | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BENL_S4_COPA_To_Tableau_Routing | Yes | RTR (Elena) | S4 | HTTPS | CPI | Process Direct | S4 Program Delta Load - 05:15AM CET | ZFI_SEND_COPA_DETAILS | Z1001_S4_BE_COPA_To_Tableau Z2001_S4_NL_COPA_To_Tableau | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z1001_S4_BE_COPA_To_Tableau | Yes | RTR (Elena) | S4 | Process Direct | Tableau | JDBC | S4 Program Delta Load - 05:15AM CET | ZFI_SEND_COPA_DETAILS | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z2001_S4_NL_COPA_To_Tableau | Yes | RTR (Elena) | S4 | Process Direct | Tableau | JDBC | S4 Program Delta Load - 05:15AM CET | ZFI_SEND_COPA_DETAILS | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BENL_S4_DELIVERY_To_Tableau | Yes | OTC | S4 | Odata | Tableau CPI | JDBC Process Direct | S4 Program Delta Load NL - 3:30AM CET Delta Load BE - 5:15AM CET | ZSD_SEND_TABLEAU_DEL_DETAILS | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BENL_S4_DELIVERY_To_Tableau_ReadSQL | Yes | OTC | S4 | Process Direct | Tableau | JDBC | S4 Program Delta Load NL - 3:30AM CET Delta Load BE - 5:15AM CET | ZSD_SEND_TABLEAU_DEL_DETAILS | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_NL_S4_PRICING_To_Tableau | Yes | OTC | S4 | Odata | Tableau | JDBC | CPI Timer Delta Load - 4:00AM CET | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_BE_S4_PRICING_To_Tableau | Yes | OTC | S4 | Odata | Tableau | JDBC | CPI Timer Delta Load - 4:00AM CET | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4H_InvoiceBilling_To_SalesForce | Yes | OTC | S4 | Odata | Salesforce | Salesforce | S4 Program Delta Load - 3:30AM CET | ZSD_SALESFORCE_BILLING_EU | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_NL_S4H_OpiumDeliveries_To_SalesForce | Yes | OTC | S4 | Odata | Salesforce | Salesforce | S4 Program Delta Load -3:30AM CET | ZSD_SEND_DELV_SALESFORCE | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BE_S4_SalesOrder_To_Tableau | Yes | OTC | S4 | Odata | Tableau | JDBC | S4 Program Delta Load - 5:15AM CET | ZSD_SEND_TABLEAU_SAL_DETAILS | NA | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_AUV_Webshop_Product_ColourCode | Yes | OTC | Tableau | JDBC | Tableau | JDBC | CPI Timer Full Load - 7:00AM CET | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_MasterData_Product_SF_To_MSSQL_FullLoad | Yes | PTP(Baskaran) | Tableau | JDBC | Salesforce | Salesforce | CPI Timer Full Load - 5:00AM CET | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_AUV_SQL_Product_Report_Evidensia | Yes | OTC | Tableau | JDBC | Evidensia | SFTP | CPI Timer Full Load - 10:00PM | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_EU_S4_Invoice_To_Evidensia | Yes | OTC | S4 | Process Direct | Evidensia | SFTP | S4 Program Delta Load - 5:15AM CET | ? | Z_CPI_IDoc_CommonFlow | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_AUV_Webshop_Overzichten | Yes | OTC | Kentico | JDBC | Email | Mail | CPI Timer ?? Load - 6:00AM CET | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_BE_EHealth_SalesOrder_To_S4 | Yes | OTC | Ehealth | AS2 | S4 | SOAP | Sender Real Time Sends order only on Wednesday | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_BE_S4_SalesOrderConfirmation_To_EHealth | Yes | OTC | S4 | Process Direct | EHealth | AS2 | S4 Real Time | NA | Z_EU_S4_SalesOrderResponse_To_Webshops3PL | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BE_S4_DeliveryNote_To_Ehealth | No | OTC | S4 | Process Direct | EHealth | AS2 | S4 | ? | Z_CPI_IDoc_CommonFlow | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BE_Netorder_SalesOrderSimulate_To_S4 | Yes | OTC | NetOrder | HTTPS | S4 | Odata | Sender Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_BE_Netorder_SalesOrder_To_S4 | Yes | OTC | NetOrder | SOAP | S4 | SOAP | Sender Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_BE_S4_InventoryOutbound_To_NetOrder | Yes | OTC | S4 | Process Direct | NetOrder | SFTP | S4 Real Time | ? | Z_CPI_IDoc_CommonFlow | TBD / No need to undeploy as there will be no trigger from S4 | NA |  | Yes
Z_BE_S4_DeliveryConfirmation_To_NetOrder | Yes | OTC | S4 | Process Direct | NetOrder | SFTP | S4 Real Time | ? | Z_CPI_IDoc_CommonFlow | TBD / No need to undeploy as there will be no trigger from S4 | NA |  | Yes
Z_BE_S4_FreeGoods_To_NetOrder | No | OTC | S4 | Process Direct | NetOrder | SFTP | S4 Real Time | ? | Z_CPI_IDoc_CommonFlow | TBD / No need to undeploy as there will be no trigger from S4 | NA |  | Yes
Z_BE_S4_MaterialDetermination_To_NetOrder | Yes | OTC | S4 | Process Direct | NetOrder | SFTP | S4 Real Time | ? | Z_CPI_IDoc_CommonFlow | TBD / No need to undeploy as there will be no trigger from S4 | NA |  | Yes
Z_NL_Kentico_SalesOrder_To_S4 | Yes | OTC | Kentico | HTTPS | S4 | SOAP | Sender Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_Kentico_SARandATP_To_S4 | Yes | OTC | Kentico | HTTPS | S4 | RFC | Sender Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4_MSDContract_To_Kentico | Yes | OTC | S4 | Odata | Kentico | SOAP | CPI Timer 6:00AM CET | NA | NA | 10/24-Interface should NOT be undeployed, as its related to Price Aggreement Interface. Alert email will be received on Sat and Sunday 11/7-It should run on Sunday. Monitor the interface | NA
Z_NL_SalesForce_ProductDesc_To_Kentico | Yes | PTP(Baskaran) | SalesForce | SOAP, HTTP | Kentico | SOAP | CPI Timer 11:30PM CET | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_EU_S4_ListingAndExclusion_To_Webshops | Yes | OTC | S4 | Process Direct | NetOrder, Kentico | SFTP, SOAP | S4 Real Time | NA | Z_CPI_IDoc_CommonFlow | TBD / No need to undeploy as there will be no trigger from S4 | NA |  | Yes
Z_EU_S4_MaterialMaster_To_Webshops | Yes | OTC | S4 | Process Direct | NetOrder, Kentico | SFTP, SOAP | S4 Program Monday to Friday Every Hour from 8:00AM CET to 7:00PM CET | ? | Z_CPI_IDoc_CommonFlow | TBD / No need to undeploy as there will be no trigger from S4 | NA |  | Yes
Z_EU_S4_PriceConditions_To_Webshop | Yes | OTC | S4 | Process Direct | NetOrder, Kentico | SFTP, SOAP | S4 Program Monday to Friday Every Hour from 8:20AM CET to 7:20PM CET | ? | Z_CPI_IDoc_CommonFlow | TBD / No need to undeploy as there will be no trigger from S4 | NA |  | Yes
Z_EU_S4_Customer_To_Webshop | Yes | OTC | S4 | Idoc | NetOrder, Kentico | SFTP, SOAP | S4 Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_EU_S4_SalesOrderResponse_To_Webshops3PL | Yes | OTC | S4 | SOAP | NetOrder, Kentico, MSD, Ehealth | SFTP, SOAP, SFTP, Process Direct | S4 Real Time | ? | Connected to Multiple iFlows using Process Direct | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4_248_Goods Receipt_To_3PL | Yes | EWM | S4 | Idoc | 3PL | SFTP | S4 Real Time | NA | Z_CPI_IDoc_CommonFlow Z_NL_ZWMMBID02_EXT_252_248_Dispatcher | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_NL_S4_246_Delivery_To_3PL | Yes | OTC | S4 | Idoc | 3PL | SFTP | S4 Real Time | NA | Z_CPI_IDoc_CommonFlow Z_NL_S4_DESADV_DELVRY07_Dispatcher | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_NL_S4_252_StockAdjustment_To_3PL | Yes | EWM | S4 | Idoc | 3PL | SFTP | S4 Real Time | NA | Z_CPI_IDoc_CommonFlow Z_NL_ZWMMBID02_EXT_252_248_Dispatcher | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_NL_S4_DESADV_DELVRY07_Dispatcher | Yes |  | S4 | Idoc | 3PL | Process Direct | S4 Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4_ZDELVRY07_DESADV_Dispatcher | Yes |  | S4 | Idoc | 3PL | Process Direct | S4 Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_ZWMMBID02_EXT_252_248_Dispatcher | Yes | EWM | S4 | Idoc | 3PL | Process Direct | S4 Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4_Delivery_To_Carrier | Yes | EWM | S4 | Process Direct | Carrier | SFTP | S4 Program Real Time | ? | Z_CPI_IDoc_CommonFlow Z_NL_S4_ZDELVRY07_DESADV_Dispatcher | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_NL_S4_Delivery_To_EPackingSlip | Yes | PTP(Baskaran) | S4 | Process Direct | EPackingSlip | SFTP | S4 Program Real Time | ? | Z_CPI_IDoc_CommonFlow Z_NL_S4_ZDELVRY07_DESADV_Dispatcher | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_EU_S4_254_ReturnOrderResponse_To_MSD | Yes | OTC | S4 | SOAP | MSD | SFTP | S4 Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_MSD_162_PriceAgreement_To_S4 | Yes | OTC | MSD | SFTP | S4 | SOAP | CPI SFTP Poll Every 15min between 5:00 to 11:00PM CET | NA | NA | 10/24-Interface should NOT be undeployed. CPI should pick up the file and it will move the file to /archive. The data will not be sent to S4 because it will be down. Alert email will be received on Sat and Sunday Latest file process to S4 11/7-Move Sunday's file from Archive to origional folder and let it process on Sunday | NA
Z_NL_MSD_245_SalesOrder_To_S4 | Yes | OTC | MSD | SFTP | S4 | SOAP | CPI SFTP Poll Every 1min | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_MSD_247_PurchaseOrder_To_S4 | Yes | PTP(Baskaran) | MSD | SFTP | S4 | SOAP | CPI SFTP Poll Every 1min | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4_250_Inventory_To_3PL_MSD_Alfasan | Yes | EWM | S4 | Idoc | MSD, Alfasan | SFTP, Mail | S4 Program Twice a Day at 3:00AM CET and 11:00 am CET | NA | Z_CPI_IDoc_CommonFlow | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_NL_S4_PurchaseOrders_To_Hills | Yes | PTP(Baskaran) | CPI | Process Direct | Hills | SFTP | S4 Program Real Time | ? | Z_CPI_IDoc_CommonFlow Z_NL_S4H_Orders_Dispatcher | TBD / No need to undeploy as there will be no trigger from S4 | NA
Z_BE_Pyramid_ProcessLog_To_Email | Yes | OTC | Pyramid | SFTP | Email | Mail | CPI SFTP Poll Every 1 hour | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_BE_S4_Invoice_To_Pyramid | Yes | OTC | S4 | HTTPS | Pyramid | SFTP | S4 Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_CPI_IDoc_CommonFlow | Yes |  | S4 | Idoc | Multiple | Process Direct | S4 Program ? | ? | Connected to Multiple iFlows using Process Direct | Should be undeployed during upgrade | Yes |  | Yes
Z_EU_S4_FMD_To_Movilitas_Sync | Yes | EWM | S4 | HTTPS | Movilitas | HTTP | S4 Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_Pagero_ASN_To_S4 | Yes | PTP(Baskaran) | Pagero | AS2 | S4 | Idoc | Sender Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4H_Orders_Dispatcher | Yes | PTP(Baskaran) | CPI | Process Direct | Pagero, Hills | Process Direct | S4 Program Real Time | ? | Z_CPI_IDoc_CommonFlow | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4_Orders_To_Pagero | Yes | PTP(Baskaran) | CPI | Process Direct | Pagero | AS2 | S4 Program Real Time | ? | Z_CPI_IDoc_CommonFlow Z_NL_S4H_Orders_Dispatcher | TBD / No need to undeploy as there will be no trigger from S4 | NA
ZOETIS_S4H_SalesOrder_BE | No | OTC | Zoetis | SFTP | S4 | SOAP | CPI SFTP Poll Every 8 hours from 6:00AM till 24:00 CET | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4_To_Vanasoft_PhysicalInventory | Yes | EWM | S4 | HTTPS | VanaSoft | HTTP | S4 Program Real Time | ? | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4_To_Vanasoft_ProductMaster | Yes | EWM | S4 | HTTPS | VanaSoft | HTTP | S4 Program Real Time | ? | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4_To_Vanasoft_StockSnapshot | Yes | EWM | S4 | HTTPS | VanaSoft | HTTP | S4 Program Real Time | ? | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_S4_To_Vanasoft_WorkOrder | Yes | EWM | S4 | HTTPS | VanaSoft | HTTP | S4 Program Real Time | ? | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_Vanasoft_To_S4_InboundCommon | Yes | EWM | VanaSoft | HTTPS | CPI | Process Direct | Sender Real Time | NA | Z_NL_Vanasoft_To_S4_WorkOrderConfirmation | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_Vanasoft_To_S4_WorkOrderConfirmation | Yes | EWM | CPI | Process Direct | S4 | HTTP | Sender Real Time | NA | NA | Should be undeployed during upgrade | Yes |  | Yes
Z_NL_MasterData_User_SF_To_MSSQL | [6 empty] | CPI Run Once

## Timeline
| Friday | Friday | Friday | Friday | Friday | Friday | Friday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Saturday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday | Sunday
| 18:00 | 19:00 | 20:00 | 21:00 | 22:00 | 23:00 | 24:00 | 25:00 | 26:00 | 27:00 | 28:00 | 29:00 | 30:00 | 31:00 | 32:00 | 33:00 | 34:00 | 35:00 | 36:00 | 37:00 | 38:00 | 39:00 | 40:00 | 41:00 | 42:00 | 43:00 | 44:00 | 45:00 | 46:00 | 47:00 | 48:00 | 49:00 | 50:00 | 51:00 | 52:00 | 53:00 | 54:00 | 55:00 | 56:00 | 57:00 | 58:00 | 59:00 | 60:00 | 61:00 | 62:00 | 63:00 | 64:00 | 65:00 | 66:00 | 67:00 | 68:00 | 69:00 | 70:00 | 71:00 | 72:00
[22 empty] | Basis - Ashish | [14 empty] | Functional validation | [6 empty] | Smoke test
Back-up
SUM
Post-Processing
Downtime | Backup |  | 5 | hrs
| SUM |  | 6 | hrs
| Post-Process |  | 10 | hrs
| Total |  | 21

## Post_Upgrade_TR
Time Interval | 03.09.25 | 07.11.25
Sr.No | Date | Time | Request | Clt | Owner | TR Imported User | Short Text | Checked | Remarks
1 |  |  | SE1K900651 | 100 | NL_SARIS |  | SPAU TR - merged | Yes | New TOC for SPAU
2 | 06.11.25 | 16:00:43 | SE1K900650 | 100 | NL_SARIS | EX_BAMANEA | Security TOC TRs | Yes | New Security ToC
3 | 03.09.25 | 15:42:48 | SE1K900098 | 100 | TM_CHALAMALS | EX_BAMANEA | TOC-Basis Note 3029446-[S4 Upgrade]: | Yes
4 | 04.09.25 | 04:17:07 | D58K900130 | 100 | SSAMALA | EX_BAMANEA | SP2: invoice solutions_fiori_perspect | Yes
5 | 04.09.25 | 04:17:08 | D53K901316 | 100 | RKASIM | EX_BAMANEA | Invoice Solution : 23.4 SPS2 Perspect | Yes
6 | 04.09.25 | 04:17:09 | Q53K900014 | 100 | RKASIM | EX_BAMANEA | Post Installation Customizing for 23. | Yes
7 | 04.09.25 | 04:17:10 | D53K901328 | 100 | SSAMALA | EX_BAMANEA | VIM 23.4 SPS2 Invoice Life Cycle card | Yes
8 | 09.09.25 | 13:01:33 | SE1K900247 | 100 | RO_MARTINC | EX_BAMANEA | Snote 3574199 delete LVTW01 form LIV0 | Yes
9 | 16.09.25 | 08:49:59 | SE1K900266 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-351 Dumpwhen printing HU | Yes
10 | 16.09.25 | 10:49:18 | SE1K900267 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-351 Dumpwhen printing HU | Yes
11 | 18.09.25 | 12:06:48 | SE1K900278 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM Retrofit DE1 to SE1 | Yes
12 | 19.09.25 | 07:36:53 | SE1K900276 | 100 | NL_SARIS | EX_BAMANEA | New Migration Objects - MDM | Yes
13 | 19.09.25 | 13:03:14 | SE1K900281 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-565 Express Document dur | Yes
14 | 19.09.25 | 14:45:08 | SE1K900282 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-565 Express Document dur | Yes
15 | 19.09.25 | 15:23:08 | SE1K900284 | 100 | FL_MOUSLIMA | EX_BAMANEA | TOC EWM S4UP-565 Express Document dur | Yes
16 | 22.09.25 | 08:15:48 | SE1K900289 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-565 Express Document dur | Yes
17 | 22.09.25 | 12:19:36 | SE1K900294 | 100 | EX_BAMANEA | EX_BAMANEA | TOC : S4UP-495 Open Fiori Application | Yes | This TR needs to be imported by Vipin
18 | 22.09.25 | 17:24:45 | SE1K900295 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-565 Express Document dur | Yes
19 | 23.09.25 | 09:59:16 | SE1K900297 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-655 ABAP after filling i | Yes
20 | 23.09.25 | 10:00:35 | SE1K900298 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-648 TU Creation Program | Yes
21 | 23.09.25 | 14:03:31 | SE1K900310 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-621 Execute counting via | Yes
22 | 23.09.25 | 15:21:37 | SE1K900313 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-664 Inbound Delivery Fio | Yes
23 | 23.09.25 | 15:23:47 | SE1K900314 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-664 Inbound Delivery Fio | Yes
24 | 24.09.25 | 08:11:51 | SE1K900315 | 100 | NL_MAZILUELE | EX_BAMANEA | S4H UPG - BUG Fix -﻿ Error GLT2201 - | Yes
25 | 24.09.25 | 09:38:37 | SE1K900317 | 100 | RO_MARTINC | EX_BAMANEA | OCT EU v_nln mapping correction S4UP- | Yes
26 | 24.09.25 | 10:53:13 | SE1K900319 | 100 | RO_MARTINC | EX_BAMANEA | OTC EU PRAT fields labels S4UP-985 | Yes
27 | 24.09.25 | 11:58:14 | SE1K900321 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-844 Cursor issue in RFUI | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
28 | 25.09.25 | 07:00:46 | SE1K900326 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-844 Cursor issue in RFUI | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
29 | 25.09.25 | 10:55:02 | SE1K900327 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-1148 HU dissapears after | Yes
30 | 25.09.25 | 12:36:49 | SE1K900330 | 100 | RO_MARTINC | EX_BAMANEA | OTC EU skip 007 message in OBA5 S4UP- | Yes
31 | 25.09.25 | 13:15:32 | SE1K900334 | 100 | TM_BOBBALAH | EX_BAMANEA | OTC_S4UP-1147_Data element change in | Yes
32 | 29.09.25 | 14:01:18 | SE1K900353 | 100 | RO_MARTINC | EX_BAMANEA | OTC BE Assign B05 reason to BE01 BE03 | Yes
33 | 01.10.25 | 10:26:54 | SE1K900328 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V1 | Yes
34 | 01.10.25 | 10:26:55 | SE1K900332 | 100 | RO_COSTEAA | EX_BAMANEA | R2R Fiori activation 2 V1 | Yes
35 | 01.10.25 | 12:39:58 | SE1K900367 | 100 | RO_MARTINC | EX_BAMANEA | OTC EU VBAK-ZZ1_ZANZPK_SDH screen 830 | Yes
36 | 02.10.25 | 03:45:13 | SE1K900371 | 100 | RO_COSTEAA | EX_BAMANEA | ToC SE1K900366 Short dumps, class ZCL | Yes
37 | 02.10.25 | 11:39:07 | SE1K900380 | 100 | NL_SARIS | EX_BAMANEA | OTC - Service Activation ToC - S4UP-1 | Yes
38 | 03.10.25 | 08:38:06 | SE1K900383 | 100 | NL_SARIS | EX_BAMANEA | MDM - S4H Migration Project - S4UP-12 | Yes
39 | 03.10.25 | 11:43:11 | SE1K900387 | 100 | NL_SARIS | EX_BAMANEA | OTC - Sales document number is cleare | Yes
40 | 03.10.25 | 11:52:26 | SE1K900389 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V2 | Yes
41 | 03.10.25 | 11:52:28 | SE1K900372 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V2 | Yes
42 | 03.10.25 | 15:33:42 | SE1K900399 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-1264 Picking of short ex | Yes
43 | 03.10.25 | 15:46:05 | SE1K900407 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-1260 Picking of short ex | Yes | Ticket raised to SAP - 1178353/2025 https://me.sap.com/case/002075129400011783532025/overview
44 | 06.10.25 | 09:11:01 | SE1K900410 | 100 | NL_SARIS | EX_BAMANEA | OTC - BO calculation bug in ATP BAPI | Yes
45 | 06.10.25 | 10:29:21 | SE1K900411 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-1029 BBD not updated OSS | Yes
46 | 06.10.25 | 10:43:23 | SE1K900381 | 100 | NL_MAZILUELE | EX_BAMANEA | RTR- S4UP-1276 - Bug Upgrade Default | Yes
47 | 06.10.25 | 13:37:54 | SE1K900420 | 100 | NL_SARIS | EX_BAMANEA | OTC - Rebate Settlements: Amounts do | Yes
48 | 06.10.25 | 15:28:45 | SE1K900422 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V3 | Yes
49 | 07.10.25 | 10:17:36 | SE1K900426 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V4 | Yes
50 | 07.10.25 | 10:17:37 | SE1K900428 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V4 | Yes
51 | 07.10.25 | 11:07:58 | SE1K900430 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-1272 QR code verifi show | Yes
52 | 07.10.25 | 13:38:16 | SE1K900431 | 100 | NL_SARIS | EX_BAMANEA | MDM - S4H Migration Project - S4UP-12 | Yes
53 | 07.10.25 | 15:09:58 | SE1K900433 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM Retrofit DE1 to SE1 | Yes
54 | 08.10.25 | 06:59:32 | SE1K900436 | 100 | NL_PATILV | EX_BAMANEA | S4HUP Configurations | Yes
55 | 08.10.25 | 06:59:33 | SE1K900369 | 100 | NL_PATILV | EX_BAMANEA | S4UP-1221 - Partner Bank Type | Yes
56 | 08.10.25 | 12:07:13 | SE1K900446 | 100 | NL_PATILV | EX_BAMANEA | S4UP-1308 - Index Data Determination | Yes
57 | 08.10.25 | 12:56:54 | SE1K900450 | 100 | EX_BALACHANA | EX_BAMANEA | TOC S4UP-1311 printing in piece pick | Yes
58 | 08.10.25 | 15:23:10 | SE1K900453 | 100 | RO_COSTEAA | EX_BAMANEA | R2R App Currency Exchange Rates (F361 | Yes
59 | 08.10.25 | 15:23:12 | SE1K900451 | 100 | RO_COSTEAA | EX_BAMANEA | R2R App Currency Exchange Rates (F361 | Yes
60 | 09.10.25 | 09:16:21 | SE1K900463 | 100 | EX_SRINIVASB | EX_BAMANEA | S4UP-1315 SAPNOTE 3612282 - F2358 Mon | Yes
61 | 09.10.25 | 11:19:08 | SE1K900465 | 100 | EX_BALACHANA | EX_BAMANEA | TOC S4UP-1183 Manual WT Creation in I | Yes | Ticket raised to SAP - 1163990/2025 https://me.sap.com/case/002075129400011639902025/overview
62 | 09.10.25 | 12:41:54 | SE1K900474 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes
63 | 09.10.25 | 14:19:41 | SE1K900479 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
64 | 10.10.25 | 10:13:28 | SE1K900480 | 100 | NL_PATILV | EX_BAMANEA | S4UP-1221 - NPO Configruation | Yes
65 | 10.10.25 | 13:41:30 | SE1K900488 | 100 | NL_SARIS | EX_BAMANEA | OTC - BO calculation bug in ATP BAPI | Yes
66 | 13.10.25 | 11:49:59 | SE1K900496 | 100 | RO_MARTINC | EX_BAMANEA | OTC EU missing stock alloc date field | Yes
67 | 13.10.25 | 14:19:06 | SE1K900493 | 100 | NL_PATILV | EX_BAMANEA | S4UP: PO Configuration | Yes
68 | 14.10.25 | 14:24:02 | SE1K900500 | 100 | NL_PATILV | EX_BAMANEA | S4UP - PO Configuration II | Yes
69 | 15.10.25 | 14:47:41 | SE1K900506 | 100 | NL_PATILV | EX_BAMANEA | S4UP-1332 PO BDC Configuration | Yes
70 | 20.10.25 | 13:56:11 | SE1K900520 | 100 | NL_PATILV | EX_BAMANEA | S4UP-1338 COA Download/Upload | Yes
71 | 20.10.25 | 13:56:13 | SE1K900524 | 100 | RO_COSTEAA | EX_BAMANEA | VIM - /OPT/AR_COA Excel export issue | Yes
72 | 21.10.25 | 10:35:52 | SE1K900529 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
73 | 21.10.25 | 11:34:18 | SE1K900536 | 100 | EX_BALACHANA | EX_YADAVV | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
74 | 22.10.25 | 09:52:23 | SE1K900532 | 100 | RO_COSTEAA | EX_BAMANEA | VIM: Vendor material number not popul | Yes
75 | 23.10.25 | 07:48:34 | SE1K900541 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
76 | 23.10.25 | 10:44:36 | SE1K900544 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
77 | 23.10.25 | 13:46:20 | SE1K900489 | 100 | RO_COSTEAA | EX_BAMANEA | VIM - App Create Annual Sales listing | Yes | Import these both TR together
78 | 24.10.25 | 08:28:14 | SE1K900555 | 100 | RO_COSTEAA | EX_BAMANEA | VIM - App Create Annual Sales listing | Yes
79 | 23.10.25 | 14:27:44 | SE1K900549 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
80 | 23.10.25 | 14:40:04 | SE1K900550 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
81 | 23.10.25 | 15:11:30 | SE1K900551 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
82 | 24.10.25 | 08:10:07 | SE1K900554 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
83 | 24.10.25 | 09:18:48 | SE1K900512 | 100 | NL_MAZILUELE | EX_BAMANEA | S4UP-1255 - DRC - BE - Annual Sales L | Yes
84 | 24.10.25 | 09:26:07 | SE1K900557 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
85 | 24.10.25 | 09:29:40 | SE1K900558 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
86 | 24.10.25 | 09:34:28 | SE1K900559 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
87 | 24.10.25 | 11:15:19 | SE1K900560 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
88 | 24.10.25 | 12:23:10 | SE1K900562 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
89 | 24.10.25 | 12:45:06 | SE1K900563 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
90 | 24.10.25 | 12:54:23 | SE1K900564 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
91 | 24.10.25 | 13:11:34 | SE1K900565 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
92 | 24.10.25 | 13:50:34 | SE1K900566 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
93 | 24.10.25 | 14:09:21 | SE1K900567 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
94 | 24.10.25 | 14:49:42 | SE1K900568 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
95 | 24.10.25 | 15:06:48 | SE1K900569 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
96 | 25.10.25 | 10:23:30 | SE1K900572 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
97 | 27.10.25 | 08:42:03 | SE1K900578 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
98 | 27.10.25 | 15:55:07 | SE1K900504 | 100 | EX_BAMANEA | EX_BAMANEA | S4UP 1334 - VIM Capture Learning Data | Yes | This TR needs to be imported by Vipin
99 | 28.10.25 | 09:27:33 | SE1K900579 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU S4UP-844 RFUI Cursor Issue | Yes
101 | 28.10.25 | 14:31:17 | SE1K900586 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU S4UP-844 RFUI Cursor Issue | Yes
107 | 31.10.25 | 11:32:35 | SE1K900391 | 100 | NL_PATILV | EX_YADAVV | S4UP-1255 - Activation GLO_DRC Functi | Yes
108 | 03.11.25 | 04:47:32 | SE1K900608 | 100 | NL_PATILV | EX_BAMANEA | S4UP- PO VIM Configurations | Yes
114 | 04.11.25 | 15:18:04 | SE1K900634 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU S4UP-844 RFUI Cursor Issue | Yes
122 | 06.11.25 | 10:01:03 | SE1K900648 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU S4UP-844 RFUI Cursor Issue | Yes
123 | 06.11.25 | 12:14:23 | SE1K900652 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU S4UP-844 RFUI Cursor Issue | Yes
124 | 06.11.25 | 15:49:31 | SE1K900655 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU S4UP-844 RFUI Cursor Issue | Yes
126 | 07.11.25 | 09:15:19 | SE1K900660 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU NEW ITS SERVICE | Yes
127 | 07.11.26 | 09:15:20 | SE1K900661 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU NEW ITS SERVICE | Yes
128 |  |  | SE1K900665 | 100 | FL_MOUSLIMA | EX_BAMANEA | EWM_DE1 TO QE1 via SE1 | Yes
129 |  |  | SE1K900666 | 100 | RO_COSTEAA | EX_BAMANEA | SPAU adjustment | Yes
130 |  |  | SE1K900667 | 100 | ex_yadavv | EX_BAMANEA | Secuirty correction TR | Yes
131 |  |  | SE1K900671 | 100 | NL_PATILV |  | S4UP: NPO Autoposting Issue | Yes
132 |  |  | SE1K900675 | 100 | EX_BALACHANA | EX_BALACHANA | EWM EU Post Upgrade Bug Fix | Yes
133 |  |  | SE1K900676 | 100 | RO_COSTEAA |  | ToC DE1K916380 - VIM objects missing in SE1 | Yes
134 |  |  | SE1K900680 | 100 | EX_BALACHANA | EX_BALACHANA | EWM NL Storage Search Seq | Yes
135 |  |  | SE1K900683 | 100 | NL_PATILV |  | S4HDR-6916 - Auto Posting for BE Company Code NPO Invoices | Yes | Created on 10-11-2025
136 |  |  | SE1K900687 | 100 | EX_BALACHANA | EX_BALACHANA | EWM NL S4HDR-6920 No queue Out-MODD for pallet order Modulix | Yes
136 |  |  | SE1K900690 | 100 | FL_MOUSLIMA | EX_BALACHANA | TOC /S4HDR-6920 No queue Out-MODD for pallet order Modulix | Yes
136 |  |  | SE1K900691 | 100 | EX_BALACHANA | EX_BALACHANA | EWM NL S4HDR-6920 No queue Out-MODD for pallet order Modulix | Yes
137 |  |  | SE1K900688 | 100 | ex_yadavv | EX_BAMANEA | uth:ex_yadavv:6981:Add 01 in M_MSEG_BWE and M_MSEG_WWE
138 |  |  | SE1K900694 | 101 | ex_yadavv | EX_BAMANEA | auth : ex_yadavv:6922: added f_ukm_sgmt
139 |  |  | SE1K900696 | 102 | ex_yadavv | EX_BAMANEA | auth : ex_yadavv:6922: added f_ukm_sgmt
140 |  |  | SE1K900692 | 100 | RO_COSTEAA | EX_BAMANEA | VIM approve invoice fiori S4HDR-6927
141 |  |  | SE1K900708 | 100 | RO_COSTEAA | EX_BAMANEA | Syntax error CL_GRAC_FPM_SEARCH_ASSIST=====CP
142 |  |  | SE1K900714 | 100 | EX_BALACHANA | EX_BALACHANA | EWM NL S4HDR-6920 No queue Out-MODD for pallet order Modulix | Yes
143 |  |  | SE1K900702 | 100 | ex_yadavv | EX_BAMANEA | auth:ex_yadaavv:6926:Activated object F_KNA1_BUK
144 |  |  | SE1K900706 | 100 | RO_COSTEAA | EX_BAMANEA | VIM approve invoice fiori S4HDR-6927 +1
145 |  |  | SE1K900724 | 100 | ex_yadavv | EX_BAMANEA | EX_YADAVV auth:ex_yadavv:6928 update /OTX/PF03_WP
146 |  |  | SE1K900726 | 100 | ex_yadavv | EX_BAMANEA | EX_YADAVV auth:ex_yadavv:6928 update /OTX/PF03_WP
147 |  |  | SE1K900723 | 100 | RO_COSTEAA | EX_BAMANEA | P2P Customer Back Order Dashboard
148 |  |  | SE1K900732 | 100 | RO_COSTEAA | EX_BAMANEA | P2P Customer Back Order Dashboard
END OF ALL UPGRADE TRs

## Post Upgrade TRs_Old
LIST of TR to be imported in PE1 post upgrade (after SPAU TR)
Sr.No | TR Number | Client | Owner | User | Short Text | Checked? | Remarks
1 | SE1K900651 | 100 | NL_SARIS | EX_BAMANEA | SPAU TR - merged | Yes | New ToC
2 | SE1K900650 | 100 | EX_YADAVV | EX_BAMANEA | Security TOC TRs | Yes | New Security ToC
3 | SE1K900098 | 100 | TM_CHALAMALS | EX_BAMANEA | TOC-Basis Note 3029446-[S4 | Yes
4 | D58K900130 | 100 | SSAMALA | EX_BAMANEA | SP2: invoice solutions_fior | Yes
5 | D53K901316 | 100 | RKASIM | EX_BAMANEA | Invoice Solution : 23.4 SPS | Yes
6 | Q53K900014 | 100 | RKASIM | EX_BAMANEA | Post Installation Customizi | Yes
7 | D53K901328 | 100 | SSAMALA | EX_BAMANEA | VIM 23.4 SPS2 Invoice Life | Yes
8 | SE1K900247 | 100 | RO_MARTINC | EX_BAMANEA | Snote 3574199 delete LVTW01 | Yes
9 | SE1K900266 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-351 Dumpwhen p | Yes
10 | SE1K900267 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-351 Dumpwhen p | Yes
11 | SE1K900278 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM Retrofit DE1 to SE1 | Yes
12 | SE1K900276 | 100 | NL_SARIS | EX_BAMANEA | New Migration Objects - MDM | Yes
13 | SE1K900281 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-565 Express Do | Yes
14 | SE1K900282 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-565 Express Do | Yes
15 | SE1K900284 | 100 | FL_MOUSLIMA | EX_BAMANEA | TOC EWM S4UP-565 Express Do | Yes
16 | SE1K900289 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-565 Express Do | Yes
17 | SE1K900294 | 100 | EX_BAMANEA | EX_BAMANEA | TOC : S4UP-495 Open Fiori A | Yes | This TR needs to be imported by Vipin
18 | SE1K900295 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-565 Express Do | Yes
19 | SE1K900297 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-655 ABAP after | Yes
20 | SE1K900298 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-648 TU Creatio | Yes
21 | SE1K900310 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-621 Execute co | Yes
22 | SE1K900313 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-664 Inbound De | Yes
23 | SE1K900314 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-664 Inbound De | Yes
24 | SE1K900315 | 100 | NL_MAZILUELE | EX_BAMANEA | S4H UPG - BUG Fix -﻿ Error | Yes
25 | SE1K900317 | 100 | RO_MARTINC | EX_BAMANEA | OCT EU v_nln mapping correc | Yes
26 | SE1K900319 | 100 | RO_MARTINC | EX_BAMANEA | OTC EU PRAT fields labels S | Yes
27 | SE1K900321 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-844 Cursor iss | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
28 | SE1K900326 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-844 Cursor iss | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
29 | SE1K900327 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-1148 HU dissap | Yes
30 | SE1K900330 | 100 | RO_MARTINC | EX_BAMANEA | OTC EU skip 007 message in | Yes
31 | SE1K900334 | 100 | TM_BOBBALAH | EX_BAMANEA | OTC_S4UP-1147_Data element | Yes
32 | SE1K900353 | 100 | RO_MARTINC | EX_BAMANEA | OTC BE Assign B05 reason to | Yes
33 | SE1K900328 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V1 | Yes
34 | SE1K900332 | 100 | RO_COSTEAA | EX_BAMANEA | R2R Fiori activation 2 V1 | Yes
35 | SE1K900367 | 100 | RO_MARTINC | EX_BAMANEA | OTC EU VBAK-ZZ1_ZANZPK_SDH | Yes
36 | SE1K900371 | 100 | RO_COSTEAA | EX_BAMANEA | ToC SE1K900366 Short dumps, | Yes
37 | SE1K900380 | 100 | NL_SARIS | EX_BAMANEA | OTC - Service Activation To | Yes
38 | SE1K900383 | 100 | NL_SARIS | EX_BAMANEA | MDM - S4H Migration Project | Yes
39 | SE1K900387 | 100 | NL_SARIS | EX_BAMANEA | OTC - Sales document number | Yes
40 | SE1K900389 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V2 | Yes
41 | SE1K900372 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V2 | Yes
42 | SE1K900399 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-1264 Picking o | Yes
43 | SE1K900407 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-1260 Picking o | Yes | Ticket raised to SAP - 1178353/2025 https://me.sap.com/case/002075129400011783532025/overview
44 | SE1K900410 | 100 | NL_SARIS | EX_BAMANEA | OTC - BO calculation bug in | Yes
45 | SE1K900411 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-1029 BBD not u | Yes
46 | SE1K900381 | 100 | NL_MAZILUELE | EX_BAMANEA | RTR- S4UP-1276 - Bug Upgrad | Yes
47 | SE1K900420 | 100 | NL_SARIS | EX_BAMANEA | OTC - Rebate Settlements: A | Yes
48 | SE1K900422 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V3 | Yes
49 | SE1K900426 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V4 | Yes
50 | SE1K900428 | 100 | RO_COSTEAA | EX_BAMANEA | R2R - Fiori activation 2 V4 | Yes
51 | SE1K900430 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM S4UP-1272 QR code v | Yes
52 | SE1K900431 | 100 | NL_SARIS | EX_BAMANEA | MDM - S4H Migration Project | Yes
53 | SE1K900433 | 100 | EX_BALACHANA | EX_BAMANEA | TOC EWM Retrofit DE1 to SE1 | Yes
54 | SE1K900436 | 100 | NL_PATILV | EX_BAMANEA | S4HUP Configurations | Yes
55 | SE1K900369 | 100 | NL_PATILV | EX_BAMANEA | S4UP-1221 - Partner Bank Ty | Yes
56 | SE1K900446 | 100 | NL_PATILV | EX_BAMANEA | S4UP-1308 - Index Data Dete | Yes
57 | SE1K900450 | 100 | EX_BALACHANA | EX_BAMANEA | TOC S4UP-1311 printing in p | Yes
58 | SE1K900453 | 100 | RO_COSTEAA | EX_BAMANEA | R2R App Currency Exchange R | Yes
59 | SE1K900451 | 100 | RO_COSTEAA | EX_BAMANEA | R2R App Currency Exchange R | Yes
60 | SE1K900463 | 100 | EX_SRINIVASB | EX_BAMANEA | S4UP-1315 SAPNOTE 3612282 - | OK
61 | SE1K900465 | 100 | EX_BALACHANA | EX_BAMANEA | TOC S4UP-1183 Manual WT Cre | Yes | Ticket raised to SAP - 1163990/2025 https://me.sap.com/case/002075129400011639902025/overview
62 | SE1K900474 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
63 | SE1K900479 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
64 | SE1K900480 | 100 | NL_PATILV | EX_BAMANEA | S4UP-1221 - NPO Configruati | Yes
65 | SE1K900488 | 100 | NL_SARIS | EX_BAMANEA | OTC - BO calculation bug in | Yes
66 | SE1K900496 | 100 | RO_MARTINC | EX_BAMANEA | OTC EU missing stock alloc | Yes
67 | SE1K900493 | 100 | NL_PATILV | EX_BAMANEA | S4UP: PO Configuration | Yes
68 | SE1K900500 | 100 | NL_PATILV | EX_BAMANEA | S4UP - PO Configuration II | Yes
69 | SE1K900506 | 100 | NL_PATILV | EX_BAMANEA | S4UP-1332 PO BDC Configurat | Yes
70 | SE1K900520 | 100 | NL_PATILV | EX_BAMANEA | S4UP-1338 COA Download/Upload | Yes
71 | SE1K900524 | 100 | RO_COSTEAA | EX_BAMANEA | VIM - /OPT/AR_COA Excel export issue S4UP-1338 | Yes
72 | SE1K900529 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
73 | SE1K900536 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issu | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
74 | SE1K900532 | 100 | RO_COSTEAA | EX_BAMANEA | VIM: Vendor material number not populated on items S4UP-1333 | Yes
75 | SE1K900541 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
76 | SE1K900544 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
77 | SE1K900489 | 100 | RO_COSTEAA | EX_BAMANEA | VIM - App Create Annual Sales listing Belgium S4UP-1255 | Yes | Import these both TR together
78 | SE1K900555 | 100 | RO_COSTEAA | EX_BAMANEA | VIM - App Create Annual Sales listing Belgium S4UP-1255+ | Yes
79 | SE1K900512 | 100 | NL_MAZILUELE | EX_BAMANEA | S4UP-1255 - DRC - BE - Annual Sales Listing Report | Yes
80 | SE1K900557 | 100 | EX_BALACHANA | EX_BAMANEA | EWM EU S4UP-844 RFUI Cursor Issue | Yes | Ticket raised to SAP - 1211453/2025 https://me.sap.com/case/002075129400012114532025/overview
81 | SE1K900602 | 100 | EX_BAMANEA | EX_BAMANEA | S4UP 1334 - VIM Capture Learning Data | Yes | This TR needs to be imported by Vipin
82 | SE1K900647 | 100 | NL_PATILV | EX_YADAVV | S4UP-1255 - Activation GLO_DRC Functi |  | Incorrect TR No. SE1K900647 does not exist. Correct one SE1K900391 at Row 87
83 | SE1K900608 | 100 | NL_PATILV | EX_BAMANEA | S4UP- PO VIM Configurations | Yes
84 | SE1K900391 | 100 | NL_PATILV | EX_YADAVV | S4UP-1255 - Activation GLO_DRC Functi | Yes
| SE1K900666 | 100 | RO_COSTEAA | RO_COSTEAA | SPAU adjustment | Yes | SPAU PE1